## Sheet1
|  | CITT |  |  |  | CLIENT |  | TASK | DATE
|  | Instructional Designer | Web Developer | Graphics | Multimedia | Coordinator | Content Developer
Evaluate | Analyze | [6 empty] | Present proposal
[8 empty] | Establish meeting schedule with Client and ID/Project Manager | 2005-01-07
[8 empty] | Determine client training needs | 2005-01-13
[8 empty] | Create the Team Exchange Site with established project summary, media delivery, timeline, standard naming conventions, specifications, deliverables spreadsheet, etc. | 2005-01-10
[8 empty] | Assess technologies needed to complete project | 2005-02-10
[8 empty] | Determine the delivery media (Web, streaming, etc) | 2005-01-20
[8 empty] | Answer the following questions: 1) Who is establishing the objectives? 2) Who is going to develop content and on what time line? 3) Who will edit/proofread content? 4) Who is/are the coordinator(s)? 5) Where will the final project reside? | 2005-01-10
[8 empty] | Complete audience analysis | 2005-01-10
[8 empty] | Deliver the approved objectives for the project | NA
| Design | [6 empty] | Create project architecture/storyboard | 2005-02-17
[8 empty] | Identify projected timeline for content development (Curriculum development, tutorial development, instructional design consultation, media tutorials, etc) | 2005-02-10
[8 empty] | Provide client instruction (Video tips, etc), CITT training | NA
[8 empty] | Selecting the development team (job descriptions, roles, responsibilities, hiring) | 2005-01-13
[8 empty] | Establish specific objectives for each item in the project storyboard | NA
[8 empty] | Design the general look and feel of the template/ Design Prototype | 2005-02-19
[8 empty] | Design assessment tools to match objectives | NA
[8 empty] | Obtain testing sites (Streaming media account, web accounts, php accounts/approvals) | NA
Evaluate | Develop | [6 empty] | Develop detailed shot lists, narration, storyboards, etc. | 2005-03-17
[8 empty] | Produce content, confirm accuracy and deliver | 2005-03-14
Incorporate approved content into final mode of delivery
Approve look and feel of the project and/or commission minor revisions as allowed within the contract
[8 empty] | Development (XML, HTML, CSS, PHP, Scripting) | NA
Digitize gathered video, narration, etc.
[8 empty] | Edit multimedia/ graphics, etc. | 2005-04-12
Ensure standards compliance and accessibility
Develop online tests
| Implement | [6 empty] | Test materials with alpha groups, using the ADL Evaluation Checklists
Revise content to ensure accuracy
Incorporate changes to improve usability, content accuracy, accessibility, standards compliance, etc.
Test materials with beta groups, using the ADL Rating Scales
Incorporate changes to improve usability, content accuracy, accessibility, standards compliance, etc.